## Responsibilities
Responsibilities - Code | Understanding the Business Problem | Domain Research | Model Research | Getting started with the code | EDA_v1 | Data Preprocessing | Code_R1 | Initial Model Building | Initial Model Local Deployment | Data Balancing | Multiple Model Building | Code_R2 | Final Model Tuning | Final Model Deployment
Assigned on | Nov 15 2022 | Nov 15 2022 | Nov 16 2022 | Nov 17 2022 | Nov 17 2022 | Nov 17 2022 | Nov 18 2022 | Nov 19 2022 | Nov 19 2022 | Nov 19 2022 | Nov 20 2022 | Nov 21 2022 | Nov 22 2022 | Nov 23 2022
Anik Roy | Anik Roy |  | Anik | Anik |  | Anik |  |  |  |  | Anik |  | Anik | Anik
Arushi Gupta | Arushi Gupta |  |  |  | Arushi |  | Arushi |  | Arushi | Arushi |  | Arushi
Divyanshi Soni | Divyanshi Soni |  |  |  |  | Divyanshi
Mansi Sinha | Mansi Sinha |  |  |  | Mansi |  | Mansi | Mansi
Completed on | Nov 15 2022 | Nov 15 2022 | Nov 16 2022 | Nov 17 2022 | Nov 18 2022 | Nov 18 2022 | Nov 18 2022 | Nov 20 2022 | Nov 20 2022 | Nov 19 2022 | Nov 22 2022 | Nov 21 2022 | Nov 21 2022 | Nov 24 2022
Responsibilities - Charter | Charter_v1 | Charter_v2 | Charter_v3 | Charter_v4 | Charter_v3 + Review
Assigned on | Nov 15 2022 | Nov 16 2022 | Nov 16 2022 | Nov 18 2022
Anik Roy | Anik
Arushi Gupta |  |  | Arushi |  | Arushi
Divyanshi Soni |  | Divyanshi
Mansi Sinha |  |  |  | Mansi
Completed on | Nov 15 2022 | Nov 16 2022 | Nov 17 2022 | Nov 18 2022

## Attendance
Meeting Number | Meeting Date | Eri | Joffe | Matthew | Krithika | Sharon | Wing
1 | 2021-12-21
2 | 2022-01-04
3 | 2022-01-06
4 | 2022-01-07
5 | 2022-01-10
6 | 2022-01-11
7 | 2022-01-12
8 | 2022-01-13